## Backlog
Stories | Tasks | Done
Iteration 1
I want to be able to pan the camera around the play field. | Init Camera angle, implement click-drag panning | X
| Implement Zoom | X
| Implement limited tilting of the camera | X
I want a tool to raise and lower swaths of terrain by clicking or painting it | Have a default terrain at the beginning of the scene. | X
| Create a toolbar to one side of screen | X
| Add a raise-lower tool to the toolbar, change mousepointer when selected | X
| Brush size option on toolbar | X
| Highlight affected terrain when hovered with tool | X
| Holding left mouse button will raise terrain; right button will lower | X
I want a tool to flatten an area of terrain | Add Flatten tool to toolbar | X
| highlight square section of terrain when tool is dragged over | X
| When mousebutton is released, affected area is set to height of starting point | X
I want a tool to smooth over an area of terrain | Add smooth tool to toolbar | X
| Add Smoothing factor to toolbar | X
| highlight square section of terrain when tool is dragged over | X
| On release, area has gradients reduced by factor. | X
I want terrain texture to depend on its steepness: grassy/velvet green for flat, rocky/plastic grey for cliffs. | Set default terrain texture | X
| Have alternate terrain texture for cliffs. Find threshold for cliffs. | x
I want the edge of the playfield to look like it has a table under it. | Give terrain boundary steep drop | X
| Get placeholder model for table at bottom of drop | X | 20
Iteration 2
I want a button on the toolbar for utilities. | Add Utilities button to toolbar | X
I want to be able to create a new, flat terrain of a default height. | Add New Terrain button to utilities bar | X
| Selecting New Terrain will initialise terrain to a default height. Terrain edges will still be zero. | X
I want to be able to save the terrain that I have been working on. | Add Save button to utilities bar | X
| Make sure saves are sent to PPG Software subfolder | X
| Create a save file dialog | X
| Write a script for serializing terrain data. | X
| Have save function go through game objects, get their data and save it. | X
| Create enum for object types | X
| adjust save function to put object types in front of serialized data | X
I want to be able to load a saved terrain from disk. | Add Load button to utilities bar | X
| Create a load file dialog | X
| Write a script for deserializing terrain data and put data into TerrainData object | X
| When file is loaded, check the object type call terrain deserializing function | X
The camera should not be allowed to move beyond limits defined by the terrain size. | Add clamping script to camera with height and xz limits | X
| prevent camera from going too near xz limits if view field would go past limits | X
The rotate camera function should take the pivot from the centre of the view, not from the mouse location. | Write new function for finding center of view and use that as pivot instead | X
The game should begin on a main menu with buttons to go to the different play modes. | Create new scene for main menu | X
| Create buttons for Free Play, Schedule and Signal modes. | X
| Make GameController a persistent singleton with a prefab | X
| Clicking Free Play button should go to terrain scene | X
I should be able to exit from the terrain editor/sandbox mode to the menu. | Add Quit button to utilities bar | X
| Switch to menu scene when quit button is clicked. | X
When I quit, I want to be prompted to save if I have changed anything since my last save. | Track whether anything has changed since the last save | X
| Create 'Do you want to save' dialog | X
| On 'Yes', call save functions as though save button has been pressed. | X | 26
Iteration 3
Utilities bar should not have a 'normal' button to deselect. Instead, clicking on a button that is already selected should deselect it. Selected buttons should be highlighted | Remove Normal button | X
| Make buttons deselect when clicked on while selected. | X
| Make any selected button highlighted. | X
The Camera should zoom more smoothly; use Lerp to transition to a target position. | Change camera zoom function so that it Lerps to a target position | X
| Change other functions that change camera position change the target position for Lerping | X
Function for finding world point at zero from screen position should be unit testable. | Separate code into testable class | X
| Write tests | X
I want to be able to place a straight, flat section of track onto the terrain. | Find a usable straight section of track in the assets | X
| Find a way to customise its length. Cut into sections maybe? Or only use a part of the model? | X
| Add a Place Track button to the toolbar | X
| Change mouse cursor when tool is selected | X
| Instantiate a new section when terrain is clicked with tool. | X
| Sections in edit mode should exist from the starting point to the cursor as long as it's within terrain boundary | X
| After a second click, the section will stay in its last condition. | X
I want to be able to place a straight section of track with an incline. I want a way to control the inclination. The terrain should follow the track height | holding shift while a track section is being dragged will adjust the height of the section end according to vertical mouse movement.
| On mouseup, terrain height will change to section height along the section. | X
I want to be able to select an end of a track section that I have already placed, and adjust it. | Select a section end with right-click | X
| Allow a section to return to edit mode | X
When I save the map, any track sections I have placed should also be saved. | Each Section object needs to have an ISaveLoadable | X
the ISaveLoadable needs to be added to the Filehandler's list when the section completes deployment
the ISaveLoadable needs to be removed to the Filehandler's list when the section returns to edit mode from deployment
| A serializable IDataObject needs to be implemented for track section data. | X
When I load a map with track sections, they should be restored. | When a Section type is found during load, a new section should be instantiated | X
| LoadFromDataObject for the section's ISaveLoadable needs to restore the GameObject to the state it was in when saved. | X
Modularise Menu Behaviours a la http://unity3d.com/learn/tutorials/modules/intermediate/scripting/coding-practices | Associate ToolSelector with the toolbar | X
| Put tool behaviours on buttons | X
| call behaviours from selected button | X | 24
Iteration 4
Move the project and associated documentation onto a repository | Download and install latest version of Git | X
| Create new Github repo and commit project | X
Fix camera minimum height irregularity | Camera limiting function should have a min height from terrain instead of preventing zoom | X
| Function for moving camera should prevent camera intersecting colliders | X
I shouldn't be able to interact with scene objects if my mouse is over a UI element | Research unity UI hit problems | X
| Will probably be a matter of detecting UI hits and only reacting to mousebuttons if none found | X
Refactor/rearrange tool inputs if necessary.
When in track mode, cyan spheres should appear at the ends of each track section. These are what I want to click on to select a track end. | Add sphere meshes and colliders to section prefab | X
| Track placement tool must maintain list of track sections | X
| Tool interface must have OnSelect and OnDeselect functions | X
| Track tool's OnSelect must activate spheres on all sections | X
| Track tool's OnDeselect must deactivate spheres on all sections | X
| Change the track right-click to only select a track if the hit is on a sphere | X
I want a curved section of track to appear curved. | Create a unit testable Vertex Bender class | X
| Find equation for dual Euler Spirals from start and end points, start direction | X
| VertexBender should displace the verts of a mesh based on its position along the dual Euler Spirals | X
| In cases where the triangles move too far from the curve, new triangles should be created to approximate | X
I want a curved section of track to have an appropriate collider/set of colliders. | Get straight sections approximation of curve | X
| Deploying a curved section will create child objects each with a box collider | X
| Each collider be displaced and rotated along the track such that they cover the whole track length and overlap where necessary | X
I want to left-click a track end to begin placing a curved section of track. The track should begin at the track end I clicked on and in the direction of the existing track section. The other end should follow my mouse pointer, curving as much as it needs to. | CurvatureController should register that a track section will be curved if a straight section is clicked on | X
| Euler spiral variables determined by start posistion and mouse position etc | X
| Curved track length will be defined by CurvatureController and fed to LengthController | X
| CurveController will curve track | X
| Register a track section to be curved if any section is clicked on | X
While editing a straight section of track, if I hover over a track end bauble, the section I am editing should become curved to fit into the existing track section | Track tool will register mouse over and changed straight track to curved | X
| Use start position, bauble position and bauble track direction for spiral vars | X
| Use curvature controller to fit the track | X
I want a curved section of track to have the terrain meet its underside for its entire length once deployed. | Get straight sections approxiamtion of curve | X
| Set terrain lines as per approximation | X
I want curved sections of track to save and load properly. | Track Data object must store one or two variables defining curvature | X | 30
Iteration 5
There should only be one track section bauble at each joint. Right-clicking on it will select the last track section to be connected to it. | Instantiate baubles independently of the section | X
| Track tool must maintain list for making them visible/invisible | X
| bauble collider should only activate when section is finalized. | X
| link baubles to each track section and vice versa. | X
| The bauble's list of links should indicate direction, and also connection order | X
Refactor the reversal of track sections such that it is done entirely in the shape controller, and the track tool doesn't need to know about it. | Rewrite track tool methods using only function calls to shape controlller | X
| Have shape controller decide which end is which based on bauble links at each end | X
Loading a map containing linked track sections should allow me to use the links correctly. | Create SaveLoadable for baubles | X
| each track section should have a UID for bauble SaveLoadable to store | X
| Once the file is completely loaded and deserialized, the track tool must go through the track sections and link to bauble objects based on IDs. | X
I want to be able to place a curved track from the end of one existing section to the beginning of another. | Find equation to govern shape of a section with two different transitions | X
| Include third mode for track shape | X
| Modify vertex bender to bend models in two different parts | X
| Track tool on a bauble will change curved track to compound curve | X
I want to be able to place a buffer stop at an existing track end. | Find a model for a buffer stop and link the prefab to the track tool
Add a sub-menu for the track tool; track by default with buffer stops
single-click sub-tool on a bauble with only one link will add buffer stop.
I should not be able to place a track section in such a way that another track's ballast is disturbed. | Catergorise or list box colliders for all track sections
Check for collisions during finalization.
If a collision occurs, prevent placement and give indication of error
Have exceptions for colliders in sections at either end of this section.
Saving and loading a map with buffer stops and compound curve sections should keep them | SaveLoadable for track sections needs to include data to recreate arced track
New Saveloadable for buffer stops; need track UIDs
| The post-save linking process should include buffer stops |  | 14

## Stories 1
I want to be able to pan the camera around the play field.
I want a tool to raise and lower swaths of terrain by clicking or painting it
I want a tool to flatten an area of terrain
I want a tool to smooth over an area of terrain
I want terrain texture to depend on its steepness: grassy/velvet green for flat, rocky/plastic grey for cliffs.
I want the edge of the playfield to look like it has a table under it.

## Stories 2
I want a button on the toolbar for utilities.
I want to be able to create a new, flat terrain of a default height.
I want to be able to save the terrain that I have been working on.
I want to be able to load a saved terrain from disk.
The camera should not be allowed to move beyond limits defined by the terrain size.
The rotate camera function should take the pivot from the centre of the view, not from the mouse location.
The game should begin on a main menu with buttons to go to the different play modes.
I should be able to exit from the terrain editor/sandbox mode to the menu.
When I quit, I want to be prompted to save if I have changed anything since my last save.

## Stories 3
Utilities bar should not have a 'normal' button to deselect. Instead, clicking on a button that is already selected should deselect it. Selected buttons should be highlighted
The Camera should zoom more smoothly; use Lerp to transition to a target position.
Function for finding world point at zero from screen position should be unit testable.
I want to be able to place a straight, flat section of track onto the terrain.
I want to be able to place a straight section of track with an incline. I want a way to control the inclination. The terrain should follow the track height
I want to be able to select an end of a track section that I have already placed, and adjust it.
When I save the map, any track sections I have placed should also be saved.
When I load a map with track sections, they should be restored.
Modularise Menu Behaviours a la http://unity3d.com/learn/tutorials/modules/intermediate/scripting/coding-practices

## Stories 4
Move the project and associated documentation onto a repository
Fix camera minimum height irregularity
I shouldn't be able to interact with scene objects if my mouse is over a UI element
When in track mode, cyan spheres should appear at the ends of each track section. These are what I want to click on to select a track end.
I want a curved section of track to appear curved.
I want a curved section of track to have an appropriate collider/set of colliders.
I want to left-click a track end to begin placing a curved section of track. The track should begin at the track end I clicked on and in the direction of the existing track section. The other end should follow my mouse pointer, curving as much as it needs to.
While editing a straight section of track, if I hover over a track end bauble, the section I am editing should become curved to fit into the existing track section
I want a curved section of track to have the terrain meet its underside for its entire length once deployed.
I want curved sections of track to save and load properly.

## Stories 5
There should only be one track section bauble at each joint. Right-clicking on it will select the last track section to be connected to it.
Refactor the reversal of track sections such that it is done entirely in the shape controller, and the track tool doesn't need to know about it.
Loading a map containing linked track sections should allow me to use the links correctly.
I want to be able to place a curved track from the end of one existing section to the beginning of another.
I want to be able to place a buffer stop at an existing track end.
I should not be able to place a track section in such a way that another track's ballast is disturbed.
Saving and loading a map with buffer stops and compound curve sections should keep them

## Stories 6
Upgrade to Unity 5
Design. Seriously.
I want to be able to create a new bauble partway around a curve.
"Rail" vectors should be goverened by the same function that adds creases to the bending model
Finalising a track section should not be so slow if it doesn't need to adjust the terrain.